## Issues list
NORTH KYLE WIND FARM LIMITED
Community Liaison Group Issues Tracker |  |  |  | 2025-01-30
Ref | Meeting Date | Category | Issue | Mitigation | Priority | Responsible | Open/Closed/Note | Date closed | Notes
1 | 2024-01-10 | Roads | Construction traffic | Traffic movements in accordance with the TMP on agreed routes. |  | Richard Buckland | Open
2 | 2024-01-10 | Roads | Turbine component deliveries-travel delays | Movements in accordance with TMP, and on established routes |  | Richard Buckland | Open |  | Delivery of turbine components due to start in May 2024. First deliveries expected 20 May.
3 | 2024-01-10 | Roads | Mud on public roads | Contractor required to keep roads clean-being closely monitored by Brockwell |  | Neil Buswell | ongoing |  | Jones Brothers have engaged a local contractor Road Sweeper at least once a week
4 | 2024-01-10 | Noise | Noise from blasting | Notifications sent out to relevant stakeholders. Council have witnessed first blast from local property. Will continue to be monitored but no follow up considered necessary. |  | Ian Sloan | Closed | 2024-01-11
5 | 2024-01-10 | Site access | Jones vehicles speeding through village and littering | Jones brought this up in their daily briefs |  | Neil Buswell | Ongoing |  | Toolbox Talks have been delivered to Jones Brothers site attendees, also with the arrival of Vestas and their contractors this will continue
6 | 2024-01-10 | Public roads | Jones not giving way at the Smithy junction | NB & LN done a road survey, signage & road markings are visible, Jones also brought up in their daily briefings |  | Neil Buswell | Ongoing |  | Junction has been monitored by NB at various times, only minimal evidence of small vehicles not stopping at junction, however not atributed to North Kyle. Larger vehicles carring sludge for a land owners spreading campaign. Toolbox talks have been delivered to Jones Brothers site attendees, also with the arrival of Vestas and their contractors this will continue
7 | 2024-01-10 | Roads | Traffic lights at Chalmerston entrance not working/and up when no staff working at this entrance. | Jones confirmed these will be down by week 3 of 2024 |  | Neil Buswell | Closed | 2024-01-11
8 | 2024-02-15 | Environmental | Ayrshire Rivers Trust complaint following observation of siltation in the Pennyvennie and Burnton Burns. Following this, SEPA visited the site on 19 Feb. | Jones Bros have installed silt mitigation and this is being overseen by our ECOW. |  | Jones | Closed | 2024-05-02 | Site visit arranged and attended by North Kyle, ECoW and Jones Brothers. Good information passed and follow up information to be collated an passed to local fishing club attendees. North Kyle will continue to monitor water quality in these burns where they cross the site.
9 | 2024-02-22 | Public complaint | Disruption to stable-owner when accessing her horses | Site staff spoke to contractor to make sure this will not happen again. |  | Richard Buckland | Closed | 2024-10-14 | Closed Chalmerston entrance to all site traffic and componant deliveries which will now elimanate the risk of interface with stables.
10 | 2024-02-26 | Site access | Quad bikes on site. Reported through local landowner | Jones installing gates at different access points |  | Jones Bros | Ongoing |  | No further security incidents. Ongoing security monitoring on site by security company.
11 | 2024-03-17 | Drainage/Fencing | Local farmer reported damage to his fence and drainage affecting his fields. | Richard & Jones Bros going to meet with farmer to discuss |  | Jones | Closed | 2024-03-30 | Site meeting held with local farmer. Fence has been fixed. Drainage to be monitored.
12 | 2024-06-20 | Light Pollution | Resident complaining of light pollution from site | Reported to Jones who have moved the tower lights away from Dalmellington |  | Jones | Closed | 2024-06-26 | Jones moved the tower light away from Dalmellington and now facing down the track
13 | 2024-06-26 | Dust surpression | Dust surpression on the Chalmerston access track | Water bowser's to go over this track |  | Jones | Ongoing |  | Jones have extra water bowsers on site
14 | 2024-06-26 | Roads | Complaints of JB speeding on the Dalgig singal track road heading to HOW access | Toolbox talk done on this and a plan to put up signs to help prevent this happening |  | Jones | ongoing |  | Further enquries to ARA, implamented a 30mph speed limit on HOW to Dalgig section of single track road for North Kyle WF site traffic.
15 | 2024-08-25 | Public complaint | Complaint that the turbine deliveries are causing damage to the main wall outside their property | Structural engineer report done at the property |  | Richard Buckland | Closed | 2024-08-01
16
17
18
19
20

## Sheet2 (hidden)
High
Medium
Low